## IS480 Deadlines
Week | Date | Day | Deadline
10 | 23 Oct 18 | Tuesday | Proposal due
12 | 6 to 10 Nov 18 | Thursday to Saturday | Acceptance
1 | 10 Jan 19 | Thursday | Registration
7 to 6 | 21 to 27 Feb 19 | Thursday to Wednesday | Midterm
11 | 19 Mar 19 | Tuesday | Poster
14 to 15 | 8 to 16 Apr 19 | Monday to Tuesday | Final
Members |  | Primary Role | Secondary Role
Hani |  | Project Manager | Business Analyst
Hazirah |  | Back-end Developer | Asst PM
Farihin |  | System Architect | Asst Back-end Developer
Yi-Ting |  | Front-end Developer | Asst QA
Srav |  | Quality Assurance | Asst Front-end Developer
Wei En |  | Back-end Developer | Asst System Architect

## Start to Acceptance
Description |  | Start to Acceptance |  |  |  |  | Date | 25 August - 10 November
Description |  | Documentation | [5 empty] | Iteration No. |  | 1
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Understanding of Project from Clients | All members | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 1 | 1 | 100% | Completed
2 | Research on Project Technologies and Scope | All members | 2018-08-29 | 2018-08-31 | 2018-08-29 | 2018-08-31 | 3 | 3 | 100% | Completed
3 | Brainstorming Solution | All members | 2018-09-01 | 2018-09-02 | 2018-09-01 | 2018-09-02 | 2 | 2 | 100% | Completed
4 | Preparation of Mobile Application Wireframe | Liting | 2018-09-03 | 2018-09-05 | 2018-09-03 | 2018-09-05 | 3 | 3 | 100%
5 | Preparation of Web Application Wireframe | Farihin
6 | Research on API availables | Srav
7 | Designing and compiling PowerPoint | Hazirah, Hani | 2018-09-06 | 2018-09-07 | 2018-09-06 | 2018-09-07 | 2 | 2 | 100%
8 | Prepare | Hazirah | 2018-09-11 | 2018-09-11 | 2018-09-11 | 2018-09-11 | 1 | 1 | 100%
9 | Submit PowerPoint Presentation to Client | Hazirah | 2018-09-11 | 2018-09-11 | 2018-09-11 | 2018-09-11 | 1 | 1 | 100%
10 | Presentation to Client | All members |  |  |  |  | 1 | 1 | 100%
11 | PM Review | Hani | 2018-09-14 | 2018-09-14 |  |  | 1 | 1 | 100%
Total | [6 empty] | 15 | 15 | 900%
Comments
Description |  | Administrator Account Module | [5 empty] | Iteration No. |  | 2
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Netbeans and local database setup | All members | 2018-09-15 | 2018-09-15 |  |  | 1 | 1 | 100%
2 | Login and logout function | Farihin, Wei En | 2018-09-16 | 2018-09-18 |  |  | 3 | 1 | 300%
3 | Remember me function | Farihin, Wei En | 2018-09-16 | 2018-09-18 |  |  | 3 | 1 | 300%
4 | Login and homepage UI | Liting | 2018-09-19 | 2018-09-20 |  |  | 2 | 1 | 200%
5 | Profile Management function | Hazirah, Wei En | 2018-09-19 | 2018-09-21 |  |  | 3 | 1 | 300%
6 | Profile UI | Srav | 2018-09-22 | 2018-09-23 |  |  | 2 | 1 | 200%
7 | Writing of Test Cases | Srav, Liting | 2018-09-24 | 2018-09-24 |  |  | 1 | 1 | 100%
8 | Testing and Debugging | Hani, Hazirah | 2018-09-25 | 2018-09-25 |  |  | 1 | 1 | 100%
9 | Deployment | Farihin | 2018-09-26 | 2018-09-26 |  |  | 1 | 1 | 100%
10 | Regression Testing | Srav, Wei En | 2018-09-27 | 2018-09-28 |  |  | 2 | 1 | 200%
11 | PM Review | Hani | 2018-09-29 | 2018-09-29 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 11 | 2000%
Comments
Description |  | Player Account Module | [5 empty] | Iteration No. |  | 3
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Login and Logout Function | Farihin, Wei En | 2018-09-30 | 2018-10-02 |  |  | 3 | 1 | 300%
2 | Remember Me Function | Farihin, Wei En | 2018-09-30 | 2018-10-02 |  |  | 3 | 1 | 300%
3 | Login and Homepage UI | Liting | 2018-10-02 | 2018-10-04 |  |  | 3 | 1 | 300%
4 | Profile Management Function | Hazirah, Wei En | 2018-10-02 | 2018-10-04 |  |  | 3 | 1 | 300%
5 | Profile UI | Srav | 2018-10-04 | 2018-10-05 |  |  | 2 | 1 | 200%
6 | Writing of Test Cases | Srav, Liting | 2018-10-06 | 2018-10-06 |  |  | 1 | 1 | 100%
7 | Testing and Debugging | Hani, Hazirah | 2018-10-07 | 2018-10-07 |  |  | 1 | 1 | 100%
8 | Deployment | Farihin | 2018-10-08 | 2018-10-08 |  |  | 1 | 1 | 100%
9 | Regression Testing | Srav, Wei En | 2018-10-09 | 2018-10-10 |  |  | 2 | 1 | 200%
10 | PM Review | Hani | 2018-10-11 | 2018-10-11 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 10 | 2000%
Comments
Description |  | Private League Module | [5 empty] | Iteration No. |  | 4
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Research on Technologies | All members | 2018-10-14 | 2018-10-14 |  |  | 1 | 1 | 100%
2 | Football League Homepage UI | Liting, Srav | 2018-10-15 | 2018-10-16 |  |  | 2 | 1 | 200%
3 | Self-propose League Function | Farihin, Wei En | 2018-10-17 | 2018-10-19 |  |  | 3 | 1 | 300%
4 | Private League Homepage UI | Liting, Srav | 2018-10-19 | 2018-10-20 |  |  | 2 | 1 | 200%
5 | Private League Scoreboard Function | Farihin, Wei En | 2018-10-20 | 2018-10-22 |  |  | 3 | 1 | 300%
6 | Milestone - Proposal Due | All members | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23
7 | Private League Scoreboard UI | Liting, Hazirah | 2018-10-24 | 2018-10-26 |  |  | 3 | 1 | 300%
8 | Writing of Test Cases | Srav, Liting | 2018-10-27 | 2018-10-27 |  |  | 1 | 1 | 100%
9 | Testing and Debugging | Hani, Hazirah | 2018-10-28 | 2018-10-28 |  |  | 1 | 1 | 100%
10 | Deployment | Farihin | 2018-10-29 | 2018-10-29 |  |  | 1 | 1 | 100%
11 | Regression Testing | Srav, Wei En | 2018-10-29 | 2018-10-30 |  |  | 2 | 1 | 200%
12 | PM Review | Hani | 2018-10-31 | 2018-10-31 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 9 | 1700%
Comments
Description |  | Public League Module | [5 empty] | Iteration No. |  | 4
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | UAT 1 | All members | 2018-11-01 | 2018-11-01 |  |  | 1 | 1 | 100%
2 | Preparation for Acceptance Presentation | All members | 2018-11-02 | 2018-11-05 |  |  | 4 | 1 | 400%
3 | Acceptance Presentation | All members | 2018-11-06 | 2018-11-10 |  |  | 5 | 1 | 500%
4 | PM Review | Hani | 2018-11-10 | 2018-11-10 |  |  | 1 | 1 | 100%
Total | [6 empty] | 11 | 4 | 1100%
Comments
Formulas:
Date = DAYS([Planned End]+1,[Planned Start])
Iteration No. = DAYS([Actual End]+1,[Actual Start])

## Start to Acceptance (OLD)
Description |  | Start to Acceptance |  |  |  |  | Date | 25 August - 10 November
Description |  | Documentation | [5 empty] | Iteration No. |  | 1
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Understanding of Project from Clients | All members | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 1 | 1 | 100% | Completed
2 | Research on Project | All members | 2018-08-29 | 2018-08-31 | 2018-08-29 | 2018-08-31 | 3 | 3 | 100% | Completed
3 | Brainstorming Solution | All members | 2018-09-01 | 2018-09-03 | 2018-09-01 | 2018-09-04 | 3 | 4 | 75% | Completed
4 | Use-case Diagram | Hani, Hazirah | 2018-09-04 | 2018-09-05 |  |  | 2 | 1 | 200%
5 | Class Diagram | Srav, Liting | 2018-09-04 | 2018-09-05 |  |  | 2 | 1 | 200%
6 | Logical Diagram | Srav, Liting | 2018-09-06 | 2018-09-07 |  |  | 2 | 1 | 200%
7 | Setting-up GIT account | Hani, Hazirah | 2018-09-08 | 2018-09-08 |  |  | 1 | 1 | 100%
8 | Setting-up Deployment Server | Farihin, Wei En | 2018-09-09 | 2018-09-10 |  |  | 2 | 1 | 200%
9 | Developing Proposal Content | All members | 2018-09-11 | 2018-09-13 |  |  | 3 | 1 | 300%
10 | PM Review | Hani | 2018-09-14 | 2018-09-14 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 15 | 1575%
Comments
Description |  | Administrator Account Module | [5 empty] | Iteration No. |  | 2
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Netbeans and local database setup | All members | 2018-09-15 | 2018-09-15 |  |  | 1 | 1 | 100%
2 | Login and logout function | Farihin, Wei En | 2018-09-16 | 2018-09-18 |  |  | 3 | 1 | 300%
3 | Remember me function | Farihin, Wei En | 2018-09-16 | 2018-09-18 |  |  | 3 | 1 | 300%
4 | Login and homepage UI | Liting | 2018-09-19 | 2018-09-20 |  |  | 2 | 1 | 200%
5 | Profile Management function | Hazirah, Wei En | 2018-09-19 | 2018-09-21 |  |  | 3 | 1 | 300%
6 | Profile UI | Srav | 2018-09-22 | 2018-09-23 |  |  | 2 | 1 | 200%
7 | Writing of Test Cases | Srav, Liting | 2018-09-24 | 2018-09-24 |  |  | 1 | 1 | 100%
8 | Testing and Debugging | Hani, Hazirah | 2018-09-25 | 2018-09-25 |  |  | 1 | 1 | 100%
9 | Deployment | Farihin | 2018-09-26 | 2018-09-26 |  |  | 1 | 1 | 100%
10 | Regression Testing | Srav, Wei En | 2018-09-27 | 2018-09-28 |  |  | 2 | 1 | 200%
11 | PM Review | Hani | 2018-09-29 | 2018-09-29 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 11 | 2000%
Comments
Description |  | Player Account Module | [5 empty] | Iteration No. |  | 3
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Login and Logout Function | Farihin, Wei En | 2018-09-30 | 2018-10-02 |  |  | 3 | 1 | 300%
2 | Remember Me Function | Farihin, Wei En | 2018-09-30 | 2018-10-02 |  |  | 3 | 1 | 300%
3 | Login and Homepage UI | Liting | 2018-10-02 | 2018-10-04 |  |  | 3 | 1 | 300%
4 | Profile Management Function | Hazirah, Wei En | 2018-10-02 | 2018-10-04 |  |  | 3 | 1 | 300%
5 | Profile UI | Srav | 2018-10-04 | 2018-10-05 |  |  | 2 | 1 | 200%
6 | Writing of Test Cases | Srav, Liting | 2018-10-06 | 2018-10-06 |  |  | 1 | 1 | 100%
7 | Testing and Debugging | Hani, Hazirah | 2018-10-07 | 2018-10-07 |  |  | 1 | 1 | 100%
8 | Deployment | Farihin | 2018-10-08 | 2018-10-08 |  |  | 1 | 1 | 100%
9 | Regression Testing | Srav, Wei En | 2018-10-09 | 2018-10-10 |  |  | 2 | 1 | 200%
10 | PM Review | Hani | 2018-10-11 | 2018-10-11 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 10 | 2000%
Comments
Description |  | Private League Module | [5 empty] | Iteration No. |  | 4
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Research on Technologies | All members | 2018-10-14 | 2018-10-14 |  |  | 1 | 1 | 100%
2 | Football League Homepage UI | Liting, Srav | 2018-10-15 | 2018-10-16 |  |  | 2 | 1 | 200%
3 | Self-propose League Function | Farihin, Wei En | 2018-10-17 | 2018-10-19 |  |  | 3 | 1 | 300%
4 | Private League Homepage UI | Liting, Srav | 2018-10-19 | 2018-10-20 |  |  | 2 | 1 | 200%
5 | Private League Scoreboard Function | Farihin, Wei En | 2018-10-20 | 2018-10-22 |  |  | 3 | 1 | 300%
6 | Milestone - Proposal Due | All members | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23
7 | Private League Scoreboard UI | Liting, Hazirah | 2018-10-24 | 2018-10-26 |  |  | 3 | 1 | 300%
8 | Writing of Test Cases | Srav, Liting | 2018-10-27 | 2018-10-27 |  |  | 1 | 1 | 100%
9 | Testing and Debugging | Hani, Hazirah | 2018-10-28 | 2018-10-28 |  |  | 1 | 1 | 100%
10 | Deployment | Farihin | 2018-10-29 | 2018-10-29 |  |  | 1 | 1 | 100%
11 | Regression Testing | Srav, Wei En | 2018-10-29 | 2018-10-30 |  |  | 2 | 1 | 200%
12 | PM Review | Hani | 2018-10-31 | 2018-10-31 |  |  | 1 | 1 | 100%
Total | [6 empty] | 20 | 9 | 1700%
Comments
Description |  | Public League Module | [5 empty] | Iteration No. |  | 4
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | UAT 1 | All members | 2018-11-01 | 2018-11-01 |  |  | 1 | 1 | 100%
2 | Preparation for Acceptance Presentation | All members | 2018-11-02 | 2018-11-05 |  |  | 4 | 1 | 400%
3 | Acceptance Presentation | All members | 2018-11-06 | 2018-11-10 |  |  | 5 | 1 | 500%
4 | PM Review | Hani | 2018-11-10 | 2018-11-10 |  |  | 1 | 1 | 100%
Total | [6 empty] | 11 | 4 | 1100%
Comments
Formulas:
Date = DAYS([Planned End]+1,[Planned Start])
Iteration No. = DAYS([Actual End]+1,[Actual Start])