## Bug Metrics
Bugs Metrics | [5 empty] | Description
Iteration | Low Impact | High Impact | Critical Impact | No. of Bug(s) | Metric Score
2 | 0 | 0 | 0 | 0 | 0 | Severity | Description
3 | 0 | 0 | 0 | 0 | 0 | Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
4 | 0 | 0 | 0 | 0 | 0 | High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
5 | 0 | 0 | 0 | 0 | 0 | Critical Impact(10 points) | The system is down or is usable after a short period of time. We have to fix the bugs to continue.
6 | 0 | 0 | 0 | 0 | 0
7 | 0 | 0 | 0 | 0 | 0
8 | 0 | 0 | 0 | 0 | 0 | Mitigation Plan
9 | 0 | 0 | 0 | 0 | 0
10 | 0 | 0 | 0 | 0 | 0
11 | 0 | 0 | 0 | 0 | 0 | Points in Iteration | Action
12 | 5 | 9 | 3 | 17 | 80 | Points =< 5 | Fix during buffer time only.
13 | 0 | 0 | 0 | 0 | 0 | 5<Points<10 | Use the planned debugging time.
14 | 0 | 0 | 0 | 0 | 0 | Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
15 | 0 | 0 | 0 | 0 | 0
16 | 0 | 0 | 0 | 0 | 0
17 | 0 | 0 | 0 | 0 | 0
18 | 0 | 0 | 0 | 0 | 0 | TAKE NOTE! DO NOT CHANGE THE VALUE WITHIN THE TABLE BUGS METRICS (CALCULATOR FOR NO. OF BUG(S) AND METRIC SCORE. IT WILL BE COMPUTE AUTOMATICALLY WHEN YOU SPECIFY "SEVERITY SCORE" IN BUG LOG
Mitigation Action
Iteration | Action
1
2 | Ensure bugs are solved before the end of iteration, for the bug has a score above 5, solve it immediately
3 | Ensure bugs are solved before the end of iteration, for the bug has a score above 5, solve it immediately
4 | Ensure bugs are solved before the end of iteration, for the bug has a score above 5, solve it immediately
5 | Ensure bugs are solved before the end of iteration, for the bug has a score above 5, solve it immediately
6 | Ensure bugs are solved before the end of iteration, for the bug has a score above 5, solve it immediately

## Iteration 2
Bug Log - Iteration 2 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 3
Bug Log - Iteration 3 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 4
Bug Log - Iteration 4 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 5
Bug Log - Iteration 5 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 6
Bug Log - Iteration 6 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 7
Bug Log - Iteration 7 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 8
Bug Log - Iteration 8 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 9
Bug Log - Iteration 9 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 10
Bug Log - Iteration 10 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 11
Bug Log - Iteration 11 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 12
Bug Log - Iteration 12 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
PrivateLeagueSelectDate.java | Calendar function is not working. User enters date manually | 1 point | Srav | Solved | Srav |  |  |  | 1 point | Low | 5
PrivateLeagueTeamList.java | Duplicate private league name only throws error at the end of creation of private league | 5 point | Hani | Solved | Nurfarihin |  |  |  | 5 point | High | 9
PrivateLeagueCreate.java | User is able to submit form even if some fields is empty | 5 point | Srav | Solved | Nurfarihin |  |  |  | 10 point | Critical | 3
PrivateLeagueCreate.java | User is able to enter $, 'money' as an input in prize field | 5 point | Nurfarihin | Solved | Nurfarihin
PirvateLeagueCreate.java | Points fields does not restrict to numbers input only | 1 point | Srav | Solved | Srav
PrivateLeagueList.java | Retrieves private leagues of all Ole users when it should be for that particular user | 5 point | Nurfarihin | Solved | Nurfarihin
PrivateLeagueCreate.java | Not able to check if league name is already in use upon submitting the form | 5 point | Srav | Solved | Nurfarihin
PrivateLeagueTeamList.java | Team logo displayed is not correspondtion to team name | 1 point | Hani | Solved | Hani
PrivateLeagueSpecialsList.java | Specials retrieved is not limited to what the admin has set | 5 point | Nurfarihin | Solved | Nurfarihin
PrivateLeagueTeamList.java | Not able to associate the checkbox Id to a particular team Id | 10 point | Nurfarihin | Solved | Nurfarihin
PrivateLeagueSpecialsList.java | Not able to associate the checkbox Id to a particular special Id | 10 point | Nurfarihin | Solved | Nurfarihin
PrivateLeagueList.java | Users who has not created private league before should be able to see an message to create their first league | 1 point | Srav | Solved | Srav
| Timezone Difference changes upcoming and past matches | 5 point |  | Not Solved
Signup.java | Password is not secured in database | 5 point | Wei En | Solved | Wei En
| No pop-up message to notify user of progress (Logging in, creating leagues, etc.) | 5 point |  | Not Solved
Login.java | Volley TimeOut error preventing users from loggin in | 10 point | Hazirah | Solved | Hazirah
SideMenuBar.java | User name is not reflected | 1 point |  | Not Solved

## Iteration 13
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 14
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 15
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 16
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 17
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Iteration 18
Bug Log - Iteration 13 | [8 empty] | Severity Point Legend
File | Description of bug | Severity Point | Discovered By | Status | Solved By | Solved Date | Remark | Final Point | Severity Point | Rating | Total
[9 empty] | 1 point | Low | 0
[9 empty] | 5 point | High | 0
[9 empty] | 10 point | Critical | 0

## Config File
Solved
Not Solved
Hani
Hazirah
Nurfarihin
Srav
Wei En
YiTing