## IS480 Deadlines
Week | Date | Day | Deadline
10 | 23 Oct 18 | Tuesday | Proposal due
12 | 2018-11-10 | Thursday to Saturday | Acceptance
1 | 10 Jan 19 | Thursday | Registration
7 to 6 | 2019-02-21 | Thursday to Wednesday | Midterm
11 | 19 Mar 19 | Tuesday | Poster
14 to 15 | 8 to 16 Apr 19 | Monday to Tuesday | Final
Members |  | Primary Role | Secondary Role
Hani |  | Project Manager | Asst Front-end Developer
Hazirah |  | Back-end Developer | Asst PM
Farihin |  | System Architect | Asst Back-end Developer
Yi-Ting |  | Front-end Developer | Asst QA
Srav |  | Quality Assurance | Asst Front-end Developer
Wei En |  | Back-end Developer | Asst System Architect

## Start to Acceptance
Description |  | Start to Acceptance |  |  |  |  | Date | 28 September - 10 November
Description |  | Documentation | [5 empty] | Iteration No. |  | 0
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Gathering of Project Requirements | All members | 2018-08-28 | 2018-08-28 | 2018-08-28 | 2018-08-28 | 1 | 1 | 100% | Completed | 0 | 0
2 | Research on Project Technologies and Scope | All members | 2018-08-29 | 2018-08-31 | 2018-08-29 | 2018-08-31 | 3 | 3 | 100% | Completed | 2 | 2
3 | Brainstorming Solution | All members | 2018-09-01 | 2018-09-04 | 2018-09-01 | 2018-09-04 | 4 | 4 | 100% | Completed | 3 | 3
4 | Preparation of Mobile Application Wireframe | Liting | 2018-09-04 | 2018-09-06 | 2018-09-04 | 2018-09-06 | 3 | 3 | 100% | Completed | 2 | 2
5 | Preparation of Web Application Wireframe | Farihin | 2018-09-07 | 2018-09-09 | 2018-09-07 | 2018-09-09 | 3 | 3 | 100% | Completed | 2 | 2
6 | Research on API availables | Srav | 2018-09-10 | 2018-09-12 | 2018-09-10 | 2018-09-12 | 3 | 3 | 100% | Completed | 2 | 2
7 | Designing and Compiling PowerPoint | Hazirah, Hani | 2018-09-12 | 2018-09-14 | 2018-09-12 | 2018-09-14 | 3 | 3 | 100% | Completed | 2 | 2
8 | Submit PowerPoint Presentation to Client | Hazirah | 2018-09-14 | 2018-09-14 | 2018-09-14 | 2018-09-14 | 1 | 1 | 100% | Completed | 0 | 0
9 | Preparation of Presentation | Hazirah | 2018-09-15 | 2018-09-17 | 2018-09-15 | 2018-09-17 | 3 | 3 | 100% | Completed | 2 | 2
10 | Presentation to Client | All members | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 1 | 1 | 100% | Completed | 0 | 0
11 | PM Review | Hani | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 1 | 1 | 100% | Completed | 0 | 0
Total | [6 empty] | 15 | 15 | 100% | Completed
Comments
Description | [7 empty] | Iteration No. |  | 1
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Gathering of Project Requirements from Client | All members | 2018-09-18 | 2018-09-18 | 2018-09-18 | 2018-09-18 | 1 | 1 | 100% |  | 0 | 0
2 | Research on Project Technologies and Scope | All members | 2018-09-19 | 2018-09-21 | 2018-09-19 | 2018-09-21 | 3 | 3 | 100% |  | 2 | 2
3 | Brainstorming Solution | All members | 2018-09-22 | 2018-09-24 | 2018-09-22 | 2018-09-24 | 3 | 3 | 100% |  | 2 | 2
4 | Use Case Diagram | Hani & Srav | 2018-09-24 | 2018-09-25 | 2018-09-24 | 2018-09-25 | 2 | 2 | 100% |  | 1 | 1
5 | Class Diagram | Farihin & Yi-Ting | 2018-09-24 | 2018-09-25 | 2018-09-24 | 2018-09-25 | 2 | 2 | 100% |  | 1 | 1
6 | Logical Diagram | Wei En & Hazirah | 2018-09-24 | 2018-09-25 | 2018-09-24 | 2018-09-25 | 2 | 2 | 100% |  | 1 | 1
7 | Setting up GIT account | Hani | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 1 | 1 | 100% |  | 0 | 0
8 | Setting up AWS/Deployment server | Hazirah | 2018-09-26 | 2018-09-26 | 2018-09-26 | 2018-09-26 | 1 | 1 | 100% |  | 0 | 0
9 | Netbeans and local database setup | All members | 2018-09-27 | 2018-09-27 | 2018-09-27 | 2018-09-27 | 1 | 1 | 100% |  | 0 | 0
10 | Web Admin Log-in/Log-out Function | Farihin & Hazirah | 2018-09-28 | 2018-09-29 | 2018-09-28 | 2018-09-29 | 2 | 2 | 100% |  | 1 | 1
11 | Web Admin Log-in/Log-out UI | Yi-Ting & Srav | 2018-09-28 | 2018-09-29 | 2018-09-28 | 2018-09-29 | 2 | 2 | 100% |  | 1 | 1
12 | Writing of Test Cases | Srav | 2018-09-29 | 2018-09-29 | 2018-09-29 | 2018-09-29 | 1 | 1 | 100% |  | 0 | 0
13 | Testing and Debugging | Hani & Hazirah | 2018-09-30 | 2018-10-01 | 2018-09-30 | 2018-10-01 | 2 | 2 | 100% |  | 1 | 1
14 | Deployment | Wei En | 2018-10-02 | 2018-10-02 | 2018-10-02 | 2018-10-02 | 1 | 1 | 100% |  | 0 | 0
15 | Regression Testing | Hazirah & Farihin | 2018-10-03 | 2018-10-04 | 2018-10-03 | 2018-10-04 | 2 | 2 | 100% |  | 1 | 1
16 | PM Review | Hani | 2018-10-05 | 2018-10-05 | 2018-10-05 | 2018-10-05 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 11 | 100%
Comments
Description |  | Web Admin Portal | [5 empty] | Iteration No. |  | 2
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Web Admin Homepage UI | Yi-Ting & Srav | 2018-10-06 | 2018-10-07 | 2018-10-06 | 2018-10-07 | 2 | 2 | 100% |  | 1 | 1
2 | Web Admin CRUD Public League UI | Yi-Ting & Hani | 2018-10-08 | 2018-10-09 | 2018-10-08 | 2018-10-09 | 2 | 2 | 100% |  | 1 | 1
3 | Web Admin Public CRUD League Specials UI | Yi-Ting & Srav | 2018-10-10 | 2018-10-11 | 2018-10-10 | 2018-10-11 | 2 | 2 | 100% |  | 1 | 1
4 | Web Admin CRUD Public League Function | Farihin & Hazirah | 2018-10-06 | 2018-10-08 | 2018-10-06 | 2018-10-08 | 3 | 3 | 100% |  | 2 | 2
5 | Web Admin Public CRUD League Specials Function | Farihin & Wei En | 2018-10-09 | 2018-10-11 | 2018-10-09 | 2018-10-11 | 3 | 3 | 100% |  | 2 | 2
6 | Writing of Test Cases | Srav | 2018-10-12 | 2018-10-12 | 2018-10-12 | 2018-10-12 | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2018-10-13 | 2018-10-14 | 2018-10-13 | 2018-10-14 | 2 | 2 | 100% |  | 1 | 1
8 | Deployment | Hazirah | 2018-10-15 | 2018-10-15 | 2018-10-15 | 2018-10-15 | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2018-10-15 | 2018-10-16 | 2018-10-15 | 2018-10-16 | 2 | 2 | 100% |  | 1 | 1
10 | PM Review | Hani | 2018-10-17 | 2018-10-17 | 2018-10-17 | 2018-10-17 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 9 | 9 | 100%
Comments
Description |  | Mobile Player Account Module | [5 empty] | Iteration No. |  | 3
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Mobile Log-in/Log-out Function | Wei En & Farihin | 2018-10-18 | 2018-10-20 | 2018-10-18 | 2018-10-20 | 3 | 3 | 100% |  | 2 | 2
2 | Mobile Remember Me Function | Wei En & Farihin | 2018-10-20 | 2018-10-21 | 2018-10-20 | 2018-10-21 | 2 | 2 | 100% |  | 1 | 1
3 | Mobile Public League Function | Wei En & Hazirah | 2018-10-21 | 2018-10-23 | 2018-10-21 | 2018-10-23 | 3 | 3 | 100% |  | 2 | 2
4 | Mobile Log-in/Log-out and Remember Me UI | Yi-Ting & Srav | 2018-10-18 | 2018-10-19 | 2018-10-18 | 2018-10-19 | 2 | 2 | 100% |  | 1 | 1
5 | Mobile Homepage UI | Yi-Ting & Hani | 2018-10-20 | 2018-10-21 | 2018-10-20 | 2018-10-21 | 2 | 2 | 100% |  | 1 | 1
6 | Writing of Test Cases | Srav | 2018-10-22 | 2018-10-22 | 2018-10-22 | 2018-10-22 | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2018-10-23 | 2018-10-24 | 2018-10-23 | 2018-10-24 | 2 | 2 | 100% |  | 1 | 1
8 | Deployment | Hazirah | 2018-10-25 | 2018-10-25 | 2018-10-25 | 2018-10-25 | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2018-10-25 | 2018-10-26 | 2018-10-25 | 2018-10-26 | 2 | 2 | 100% |  | 1 | 1
10 | Proposal Documentation | Hani | 2018-10-18 | 2018-10-23 | 2018-10-18 | 2018-10-23 | 6 | 6 | 100% |  | 5 | 5
11 | Milestone - Proposal Due | All member | 2018-10-23 | 2018-10-23 | 2018-10-23 | 2018-10-23 | 1 | 1 | 100% |  | 0 | 0
12 | PM Review | Hani | 2018-10-27 | 2018-10-27 | 2018-10-27 | 2018-10-27 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 14 | 14 | 100%
Comments
Description |  | Mobile Public League | [5 empty] | Iteration No. |  | 4
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
2 | Mobile Public League View Prediction Function | Wei En & Hazirah | 2018-10-28 | 2018-10-30 | 2018-10-28 | 2018-10-30 | 3 | 3 | 100% |  | 2 | 2
3 | Mobile Public League Prediction UI | Yi-Ting & Hani | 2018-10-28 | 2018-10-30 | 2018-10-28 | 2018-10-30 | 3 | 3 | 100% |  | 2 | 2
4 | Mobile Public League View Prediction UI | Yi-Ting & Srav | 2018-10-30 | 2018-11-01 | 2018-10-30 | 2018-11-01 | 3 | 3 | 100% |  | 2 | 2
5 | Mobile Intro Slider UI | Yi-Ting & Srav | 2018-11-01 | 2018-11-03 | 2018-11-01 | 2018-11-03 | 3 | 3 | 100% |  | 2 | 2
6 | Writing of Test Cases | Srav | 2018-11-04 | 2018-11-04 | 2018-11-04 | 2018-11-04 | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2018-11-05 | 2018-11-06 | 2018-11-05 | 2018-11-06 | 2 | 2 | 100% |  | 1 | 1
8 | Deployment | Hazirah | 2018-11-06 | 2018-11-06 | 2018-11-06 | 2018-11-06 | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2018-11-07 | 2018-11-08 | 2018-11-07 | 2018-11-08 | 2 | 2 | 100% |  | 1 | 1
10 | Acceptance Slides Documentation | Hani | 2018-11-06 | 2018-11-07 | 2018-11-06 | 2018-11-07 | 2 | 2 | 100% |  | 1 | 1
11 | Acceptance Preparation | All member | 2018-11-08 | 2018-11-08 | 2018-11-08 | 2018-11-08 | 1 | 1 | 100% |  | 0 | 0
12 | Milestone - Acceptance Presentation | All member | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 1 | 1 | 100% |  | 0 | 0
13 | PM Review | Hani | 2018-11-09 | 2018-11-09 | 2018-11-09 | 2018-11-09 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 11 | 100%
Comments
Formulas:
Date = DAYS([Planned End]+1,[Planned Start])
Iteration No. = DAYS([Actual End]+1,[Actual Start])

## Acceptance to Mid-terms
Description |  | Acceptance to Mid-Terms |  |  |  |  | Date | 11 Nov 18 to 19 Feb 19
Description | [6 empty] | Iteration No. |  |  | 5
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Review of Mobile Account Management Function | Wei En & Farihin | 2018-11-11 | 2018-11-12 | 2018-11-11 | 2018-11-12 | 2 | 2 | 100% |  | 1 | 1
2 | Review of Mobile Public League Function | Hazirah & Wei En | 2018-11-12 | 2018-11-13 | 2018-11-12 | 2018-11-13 | 2 | 2 | 100% |  | 1 | 1
3 | Review of Mobile UI | Yi Ting & Hani | 2018-11-11 | 2018-11-13 | 2018-11-11 | 2018-11-13 | 3 | 3 | 100% |  | 2 | 2
4 | Review of Web Account Management Function | Hazirah & Farihin | 2018-11-12 | 2018-11-13 | 2018-11-12 | 2018-11-13 | 2 | 2 | 100% |  | 1 | 1
5 | Review of Web Admin League Function | Wei En & Farihin | 2018-11-13 | 2018-11-14 | 2018-11-13 | 2018-11-14 | 2 | 2 | 100% |  | 1 | 1
6 | Writing of Test Cases | Srav | 2018-11-14 | 2018-11-14 | 2018-11-14 | 2018-11-14 | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2018-11-15 | 2018-11-15 | 2018-11-15 | 2018-11-15 | 1 | 1 | 100% |  | 0 | 0
8 | Deployment | Hazirah | 2018-11-16 | 2018-11-16 | 2018-11-16 | 2018-11-16 | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2018-11-17 | 2018-11-18 | 2018-11-17 | 2018-11-18 | 2 | 2 | 100% |  | 1 | 1
10 | PM Review | Hani | 2018-11-19 | 2018-11-19 | 2018-11-19 | 2018-11-19 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 7 | 7 | 100%
Comments
Description | [6 empty] | Iteration No. |  |  | 6
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Sync of Web and Mobile Database | Wei En & Hazirah | 2018-11-20 | 2018-11-23 | 2018-11-20 | 2018-11-23 | 4 | 4 | 100% |  | 3 | 3
2 | Web CRUD FAQ | Farihin & Hazirah | 2018-11-23 | 2018-11-25 | 2018-11-23 | 2018-11-25 | 3 | 3 | 100% |  | 2 | 2
3 | Update Mobile Homepage UI | Yi Ting & Hani | 2018-11-20 | 2018-11-22 | 2018-11-20 | 2018-11-22 | 3 | 3 | 100% |  | 2 | 2
4 | Writing of Test Cases | Srav | 2018-11-26 | 2018-11-27 | 2018-11-26 | 2018-11-27 | 2 | 2 | 100% |  | 1 | 1
5 | Testing and Debugging | Hazirah & Wei En | 2018-11-27 | 2018-11-28 | 2018-11-27 | 2018-11-28 | 2 | 2 | 100% |  | 1 | 1
6 | Deployment | Hazirah | 2018-11-28 | 2018-11-28 | 2018-11-28 | 2018-11-28 | 1 | 1 | 100% |  | 0 | 0
7 | Regression Testing | Wei En & Farihin | 2018-11-29 | 2018-11-30 | 2018-11-29 | 2018-11-30 | 2 | 2 | 100% |  | 1 | 1
8 | PM Review | Hani | 2018-11-30 | 2018-11-30 | 2018-11-30 | 2018-11-30 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 10 | 10 | 100%
Comments
Description | [6 empty] | Iteration No. |  |  | 7
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Research on association of gambling and football | All member | 2018-12-01 | 2018-12-03 | 2018-12-01 | 2018-12-03 | 3 | 3 | 100% |  | 2 | 2
2 | Research on pros/cons of predicting football | All member | 2018-12-04 | 2018-12-06 | 2018-12-04 | 2018-12-06 | 3 | 3 | 100% |  | 2 | 2
3 | Research findings in infographic | Hani | 2018-12-07 | 2018-12-09 | 2018-12-07 | 2018-12-09 | 3 | 3 | 100% |  | 2 | 2
4 | PM Review | Hani | 2018-12-10 | 2018-12-10 | 2018-12-10 | 2018-12-10 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 6 | 6 | 100%
Comments
Description | [6 empty] | Iteration No. |  |  | 8
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Mobile Profile UI | Srav & Yi-Ting | 2018-12-11 | 2018-12-12 | 2018-12-11 | 2018-12-12 | 2 | 2 | 100% |  | 1 | 1
2 | Mobile Create Private League Function | Hazirah & Wei En | 2018-12-11 | 2018-12-14 | 2018-12-11 | 2018-12-15 | 4 | 5 | 80% |  | 3 | 4
3 | Mobile Auto-generated Access Code to Private League | Farihin & Wei En | 2018-12-15 | 2018-12-18 | 2018-12-15 | 2018-12-18 | 4 | 4 | 100% |  | 3 | 3
4 | Mobile FAQ UI | Hani & Yi-Ting | 2018-12-13 | 2018-12-14 | 2018-12-13 | 2018-12-14 | 2 | 2 | 100% |  | 1 | 1
5 | Writing of Test Cases | Srav | 2018-12-18 | 2018-12-19 | 2018-12-18 | 2018-12-18 | 2 | 1 | 200% |  | 1 | 0
6 | Testing and Debugging | Hazirah & Hani | 2018-12-19 | 2018-12-20 | 2018-12-19 | 2018-12-20 | 2 | 2 | 100% |  | 1 | 1
7 | Deployment | Hazirah | 2018-12-21 | 2018-12-21 | 2018-12-21 | 2018-12-21 | 1 | 1 | 100% |  | 0 | 0
8 | Regression Testing | Wei En & Farihin | 2018-12-21 | 2018-12-22 | 2018-12-21 | 2018-12-22 | 2 | 2 | 100% |  | 1 | 1
9 | PM Review | Hani | 2018-12-22 | 2018-12-22 | 2018-12-22 | 2018-12-22 | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 11 | 100%
Comments
Description | [6 empty] | Iteration No. |  |  | 9
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Mobile Create Private League UI | Srav & Yi-Ting | 2018-12-23 | 2018-12-26 |  |  | 4 | 1 | 400% |  | 3 | 0
2 | Mobile Join Private League UI | Hani & Yi-Ting | 2018-12-24 | 2018-12-26 |  |  | 3 | 1 | 300% |  | 2 | 0
3 | Mobile FAQ Function | Hazirah & Wei En | 2018-12-23 | 2018-12-26 |  |  | 4 | 1 | 400% |  | 3 | 0
4 | Mobile Predict Private League Function | Wei En & Farihin | 2018-12-26 | 2018-12-28 |  |  | 3 | 1 | 300% |  | 2 | 0
5 | Writing of Test Cases | Srav | 2018-12-29 | 2018-12-29 |  |  | 1 | 1 | 100% |  | 0 | 0
6 | Testing and Debugging | Hazirah & Farihin | 2018-12-30 | 2019-01-01 |  |  | 3 | 1 | 300% |  | 2 | 0
7 | Deployment | Hazirah | 2019-01-01 | 2019-01-01 |  |  | 1 | 1 | 100% |  | 0 | 0
8 | Regression Testing | Wei En & Farihin | 2019-01-02 | 2019-01-03 |  |  | 2 | 1 | 200% |  | 1 | 0
9 | PM Review | Hani | 2019-01-03 | 2019-01-03 |  |  | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 13 | 0 | #DIV/0!
Comments
Description | [6 empty] | Iteration No. |  |  | 10
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Mobile Predict Private League Function UI | Hani & Srav | 2019-01-04 | 2019-01-05 |  |  | 2 | 1 | 200% |  | 1 | 0
2 | Mobile View Private League Prediction UI | Hani & Yi-Ting | 2019-01-06 | 2019-01-07 |  |  | 2 | 1 | 200% |  | 1 | 0
3 | Mobile Public League Leaderboard UI | Yi-Ting & Srav | 2019-01-07 | 2019-01-09 |  |  | 3 | 1 | 300% |  | 2 | 0
4 | Mobile View Private League Function | Wei En & Hazirah | 2019-01-04 | 2019-01-06 |  |  | 3 | 1 | 300% |  | 2 | 0
5 | Mobile Retrieve Top Players from Public League Function | Wei En & Farihin | 2019-01-07 | 2019-01-10 |  |  | 4 | 1 | 400% |  | 3 | 0
6 | Writing of Test Cases | Srav | 2019-01-10 | 2019-01-10 |  |  | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Farihin | 2019-01-11 | 2019-01-12 |  |  | 2 | 1 | 200% |  | 1 | 0
8 | Deployment | Hazirah | 2019-01-13 | 2019-01-13 |  |  | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2019-01-14 | 2019-01-15 |  |  | 2 | 1 | 200% |  | 1 | 0
10 | PM Review | Hani | 2019-01-15 | 2019-01-15 |  |  | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 0 | #DIV/0!
Comments
Description | [6 empty] | Iteration No. |  |  | 11
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Mobile Public League Leaderboard UI | Yi-Ting & Srav | 2019-01-16 | 2019-01-18 |  |  | 3 | 1 | 300% |  | 2 | 0
2 | Update View Mobile Public League Prediction UI | Hani & Yi-Ting | 2019-01-18 | 2019-01-19 |  |  | 2 | 1 | 200% |  | 1 | 0
3 | Mobile Settings UI | Hani & Yi-Ting | 2019-01-20 | 2019-01-21 |  |  | 2 | 1 | 200% |  | 1 | 0
4 | Mobile Public Leaderboard Function | Wei En & Farihin | 2019-01-16 | 2019-01-19 |  |  | 4 | 1 | 400% |  | 3 | 0
5 | Mobile Notification Function | Wei En & Hazirah | 2019-01-19 | 2019-01-21 |  |  | 3 | 1 | 300% |  | 2 | 0
6 | Writing of Test Cases | Srav | 2019-01-21 | 2019-01-21 |  |  | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2019-01-22 | 2019-01-23 |  |  | 2 | 1 | 200% |  | 1 | 0
8 | Deployment | Hazirah | 2019-01-24 | 2019-01-24 |  |  | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2019-01-24 | 2019-01-25 |  |  | 2 | 1 | 200% |  | 1 | 0
10 | PM Review | Hani | 2019-01-25 | 2019-01-25 |  |  | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 0 | #DIV/0!
Comments
Description | [6 empty] | Iteration No. |  |  | 12
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Update Mobile Sign-up Function | Hazirah & Wei En | 2019-01-26 | 2019-01-27 |  |  | 2 | 1 | 200% |  | 1 | 0
2 | Update Mobile Log-In Function | Wei En & Farihin | 2019-01-27 | 2019-01-28 |  |  | 2 | 1 | 200% |  | 1 | 0
3 | Update View Mobile Public League Prediction Function | Farihin & Hazirah | 2019-01-28 | 2019-01-29 |  |  | 2 | 1 | 200% |  | 1 | 0
4 | Update Mobile Sign-up UI | Hani & Yi-Ting | 2019-01-30 | 2019-01-31 |  |  | 2 | 1 | 200% |  | 1 | 0
5 | Update Mobile Log-In UI | Hani & Yi-Ting | 2019-01-31 | 2019-02-01 |  |  | 2 | 1 | 200% |  | 1 | 0
6 | Writing of Test Cases | Srav | 2019-02-01 | 2019-02-01 |  |  | 1 | 1 | 100% |  | 0 | 0
7 | Testing and Debugging | Hazirah & Hani | 2019-02-02 | 2019-02-03 |  |  | 2 | 1 | 200% |  | 1 | 0
8 | Deployment | Hazirah | 2019-02-04 | 2019-02-04 |  |  | 1 | 1 | 100% |  | 0 | 0
9 | Regression Testing | Wei En & Farihin | 2019-02-04 | 2019-02-06 |  |  | 3 | 1 | 300% |  | 2 | 0
10 | UAT 1 | All members | 2019-02-06 | 2019-02-08 |  |  | 3 | 1 |  |  | 2 | 0
11 | PM Review | Hani | 2019-02-08 | 2019-02-08 |  |  | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 10 | 0 | #DIV/0!
Comments
Description | [6 empty] | Iteration No. |  |  | 13
S/N | Task | Members | Planned Start | Planned End | Actual Start | Actual End | Planned Days | Actual Days | Planned/Actual Days | Status
1 | Web Admin Retrieve Top Players Function | Farihin & Wei En | 2019-02-09 | 2019-02-11 |  |  | 3 | 1 | 300% |  | 2 | 0
2 | Web Admin Leaderboard Function | Farihin & Hazirah | 2019-02-11 | 2019-02-13 |  |  | 3 | 1 | 300% |  | 2 | 0
3 | Web Admin Leaderboard UI | Srav & Yi-Ting | 2019-02-09 | 2019-02-11 |  |  | 3 | 1 | 300% |  | 2 | 0
4 | Writing of Test Cases | Srav | 2019-02-12 | 2019-02-12 |  |  | 1 | 1 | 100% |  | 0 | 0
5 | Testing and Debugging | Hazirah & Hani | 2019-02-13 | 2019-02-14 |  |  | 2 | 1 | 200% |  | 1 | 0
6 | Deployment | Hazirah | 2019-02-15 | 2019-02-15 |  |  | 1 | 1 | 100% |  | 0 | 0
7 | Regression Testing | Wei En & Farihin | 2019-02-16 | 2019-02-18 |  |  | 3 | 1 | 300% |  | 2 | 0
8 | Documentation for Mid-Term Presentation | Hani | 2019-02-17 | 2019-02-19 |  |  | 3 | 1 | 300% |  | 2 | 0
9 | Preparation for Mid-Term Presentation | All members | 2019-02-20 | 2019-02-20 |  |  | 1 | 1 | 100% |  | 0 | 0
10 | Milestone - Mid-Term Presentation | All members | 2019-02-21 | 2019-02-21 |  |  | 1 | 1 | 100% |  | 0 | 0
11 | PM Review | Hani | 2019-02-21 | 2019-02-21 |  |  | 1 | 1 | 100% |  | 0 | 0
Total | [6 empty] | 11 | 0 | #DIV/0!
Comments
Formulas:
Date = DAYS([Planned End]+1,[Planned Start])
Actual Days = DAYS([Actual End]+1,[Actual Start])